## SI
| Fase |  | Tarefa | Data de início | Data final | Horário de calendário padrão |  |  | Linha |  | Tarefa | Duração | Pedecessora | Nome dos Recursos | Tipo de tarefa | Nome do recurso | Tipo | Unidade do Material | Taxa padrão
Projeto Integrador 1 | Planejamento | A | Levantamento de informações | 2023-02-24 | 2023-03-03 | 6a feira | 21:05 as 22:35 - turma 101 |  | 1 |  | Projeto Integrador 1 |  |  |  | Duração fixa | Breno | Trabalho |  | R$20,00/h
|  | B | Elaborar Requitos Funcionais e Requisitos não funcionais | 2023-03-03 | 2023-03-17 | Domingo | 14:00 às 15:30 |  | 2 |  | Planejamento |  |  |  |  | Gustavo | Trabalho |  | R$20,00/h
|  | C | Documentação | 2023-02-24 | 2023-03-17 |  |  |  | 3 | A | Levantamento de informações | 3h |  | Breno, Gustavo, Murilo, Pedro e Victor |  | Murilo | Trabalho |  | R$20,00/h
|  |  | Entrega da fase de Requisitos | 2023-03-20 |  | Calendário |  |  | 4 | B | Elaborar Requitos Funcionais e Requisitos não funcionais | 9h | 3 | Breno, Gustavo, Murilo, Pedro e Victor |  | Pedro | Trabalho |  | R$20,00/h
| Fase 1 Desenvolvimento | D | Elaborar o algoritmo do programa | 2023-03-24 | 2023-04-07 | 1 | 2023-02-17 | Aula | 5 | C | Documentação | 4h | 3 | Breno, Gustavo, Murilo, Pedro e Victor |  | Victor | Trabalho |  | R$20,00/h
|  | E | Efetuar a entrada de dados |  |  |  | 2023-02-19 | Atividade autônoma | 6 |  | Entrega da fase de Requisitos | 0 | 4;5 | Breno, Gustavo, Murilo, Pedro e Victor
|  | F | Classificar a qualidade do ar para os parâmetros lidos |  |  | 2 | 2023-02-24 | Feriado | 7 |  | Fase 1 Desenvolvimento
|  | G | Testar o programa |  |  |  | 2023-02-26 | Atividade autônoma | 8 | D | Elaborar o algoritmo do programa | 1.5h | 4;5 | Breno, Gustavo, Murilo, Pedro e Victor
|  |  | Entrega da Fase 1 | 2023-04-10 |  | 3 | 2023-03-03 | Aula | 9 | E | Efetuar a entrada de dados | 2h | 8 | Breno, Gustavo, Murilo, Pedro e Victor
| Fase 2 Desenvolvimento | H | Criação de conta para o banco de dados | 2023-04-14 | 2023-04-28 |  | 2023-03-05 | Atividade autônoma | 10 | F | Classificar a qualidade do ar para os parâmetros lidos | 5.5h | 9 | Breno, Gustavo, Murilo, Pedro e Victor
|  | I | Criar a tabela no banco de dados |  |  | 4 | 2023-03-10 | Aula | 11 | G | Testar o programa | 9h | 9 | Breno, Gustavo, Murilo, Pedro e Victor
|  | J | Inserir dados de amostras na tabela |  |  |  | 2023-03-12 | Atividade autônoma | 12 |  | Entrega da Fase 1 | 0 | 10;11 | Breno, Gustavo, Murilo, Pedro e Victor
|  | K | Conectar o programa no banco de dados |  |  | 5 | 2023-03-17 | Aula | 13 |  | Fase 2 Desenvolvimento
|  | L | Criar rotina para ler as amostras e calcular as médias os parâmetros |  |  |  | 2023-03-19 | Atividade autônoma | 14 | H | Criação de conta para o banco de dados | 30m | 10;11 | Breno, Gustavo, Murilo, Pedro e Victor
|  | M | Classificar a qualidade do ar para a média dos parâmetros |  |  | 6 | 2023-03-24 | Aula | 15 | I | Criar a tabela no banco de dados | 2h | 14 | Breno, Gustavo, Murilo, Pedro e Victor
|  | N | Testar o programa |  |  |  | 2023-03-26 | Atividade autônoma | 16 | J | Inserir dados de amostras na tabela | 2h | 15 | Breno, Gustavo, Murilo, Pedro e Victor
|  |  | Entrega da Fase 2 | 2023-05-01 |  | 7 | 2023-03-31 | Aula | 17 | K | Conectar o programa no banco de dados | 2h | 15 | Breno, Gustavo, Murilo, Pedro e Victor
| Fase 3 Entrega Final do Projeto | O | Criar o menu para o sistema | 2023-05-05 | 2023-05-26 |  | 2023-04-02 | Atividade autônoma | 18 | L | Criar rotina para ler as amostras e calcular as médias os parâmetros | 1.5h | 16;17 | Breno, Gustavo, Murilo, Pedro e Victor
|  | P | Criar a opção de inserir amostras |  |  | 8 | 2023-04-07 | Feriado | 19 | M | Classificar a qualidade do ar para a média dos parâmetros | 2h | 18 | Breno, Gustavo, Murilo, Pedro e Victor
|  | Q | Criar a opção de alterar 1 amostra |  |  |  | 2023-04-09 | Atividade autônoma | 20 | N | Testar o programa | 9h | 15 | Breno, Gustavo, Murilo, Pedro e Victor
|  | R | Criar a opção de excluir 1 amostra |  |  |  | 2023-04-09 | Atividade substitutiva | 21 |  | Entrega da Fase 2 | 0 | 19;20 | Breno, Gustavo, Murilo, Pedro e Victor
|  | S | Classificar a qualidade do ar para a média dos parâmetros |  |  | 9 | 2023-04-14 | Aula | 22 |  | Fase 3 Entrega Final do Projeto
|  | T | Documentação |  |  |  | 2023-04-16 | Atividade autônoma | 23 | O | Criar o menu para o sistema | 2h | 19;20 | Breno, Gustavo, Murilo, Pedro e Victor
|  | U | Testar o programa |  |  | 10 | 2023-04-21 | Feriado | 24 | P | Criar a opção de inserir amostras | 2.5h | 23 | Breno, Gustavo, Murilo, Pedro e Victor
|  |  | Entrega da Fase Final | 2023-05-29 |  |  | 2023-04-23 | Atividade autônoma | 25 | Q | Criar a opção de alterar 1 amostra | 2.5h | 24 | Breno, Gustavo, Murilo, Pedro e Victor
| Apresentação | V | Preparar a apresentação | 2023-06-02 | 2023-06-23 |  | 2023-04-23 | Atividade substitutiva | 26 | R | Criar a opção de excluir 1 amostra | 2.5h | 25 | Breno, Gustavo, Murilo, Pedro e Victor
|  | X | Treinar a apresentação |  |  | 11 | 2023-04-28 | Aula | 27 | S | Classificar a qualidade do ar para a média dos parâmetros | 2.5h | 26 | Breno, Gustavo, Murilo, Pedro e Victor
|  | W | Apresentar o sistema para Banca Examinadora |  |  |  | 2023-04-30 | Atividade autônoma | 28 | T | Documentação | 12h | 19;20 | Breno, Gustavo, Murilo, Pedro e Victor
|  |  | Fim do projeto | 2023-06-23 |  | 12 | 2023-05-05 | Aula | 29 | U | Testar o programa | 12h | 19;20 | Breno, Gustavo, Murilo, Pedro e Victor
[7 empty] | 2023-05-07 | Atividade autônoma | 30 |  | Entrega da Fase Final | 0 | 27;28;29 | Breno, Gustavo, Murilo, Pedro e Victor
[6 empty] | 13 | 2023-05-12 | Aula | 31 |  | Apresentação
[7 empty] | 2023-05-14 | Atividade autônoma | 32 | V | Preparar a apresentação | 6h | 27;28;29 | Breno, Gustavo, Murilo, Pedro e Victor
[6 empty] | 14 | 2023-05-19 | Aula | 33 | X | Treinar a apresentação | 3h | 32 | Breno, Gustavo, Murilo, Pedro e Victor
[7 empty] | 2023-05-21 | Atividade autônoma | 34 | W | Apresentar o sistema para Banca Examinadora | 9h | 33 | Breno, Gustavo, Murilo, Pedro e Victor
[6 empty] | 15 | 2023-05-26 | Aula | 35 |  | Fim do projeto | 0 | 34 | Breno, Gustavo, Murilo, Pedro e Victor
[7 empty] | 2023-05-28 | Atividade autônoma
[6 empty] | 16 | 2023-06-02 | Aula
[7 empty] | 2023-06-04 | Atividade autônoma
[6 empty] | 17 | 2023-06-09 | Feriado |  |  |  |  | Legenda
[7 empty] | 2023-06-11 | Atividade autônoma |  |  |  |  | Preenchimento deverá ser feito pelo time
[6 empty] | 18 | 2023-06-16 | Aula
[7 empty] | 2023-06-18 | Atividade autônoma
[6 empty] | 19 | 2023-06-23 | Aula
[7 empty] | 2023-06-25 | Atividade autônoma
Note on T2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O time deverá preencher a planilha de recursos
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir horário de trabalho das atividades autônomas
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O time deverá calcular a duração das tarefas
Note on Q4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades substitutivas
Note on Q22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades substitutivas
Note on Q27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on Q35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on Q36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: O Time deverá definir os recursos necessários para a tarefa
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on I43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas
Note on I45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserir as datas de atividades autônomas